## Project Schedule
Attachment E: Project Schedule
Bidder shall commit to the following schedule by inserting dates in yellow fields below, and noting any changes to vendor production/delivery dates by adding alternate date (if any) next to dates below in column E. Milestone dates shown in red and cannot be changed.
Competitive Bidding | Time | Date Range Start | Date / Date End | Alternate Date
Issue Furniture Bid to Vendors |  |  | 2013-06-21
Notice of Intent to Bid | 17:00 |  | 2013-06-25
Final Questions from Bidders | 12:00 |  | 2013-06-27
Answers to Bidders |  | 2013-07-01 | 2013-07-03
Bid Response Due | 16:00 |  | 2013-07-09
Evaluate bids, questions to Bidders |  | 2013-07-09 | 2013-07-15
Manufacturer Presentations & Showroom Tours |  | 2013-07-11 | 2013-07-12
Final Recommendations and Award |  |  | 2013-08-02
Other Bidding (replace as needed)
Post-award Planning & Production |  | Date Range Start | Date / Date End | Alternate Date
Mock-up order/production by winning bidder |  | 2013-08-08 | 2013-08-28
Mock-up installation & set up |  | 2013-08-29 | 2013-08-30
Client Mock-up evaluation |  | 2013-09-03 | 2013-09-09
Workstation/Office order placement |  | 2013-09-10 | 2013-09-12
Last day for order revisions
Furniture production |  | 2013-09-10 | 2013-11-05
Furniture Shipping/Deliveries |  | 2013-11-06 | 2013-11-11
Other Bidding (replace as needed)
Other Bidding (replace as needed)
Installation | Floor(s) | Date Range Start | Date / Date End
Floors (indicate)
Floors (indicate)
Floors (indicate)
Floors (indicate)
Floors (indicate)
Furniture Punchlist & Corrections
Other Installation (replace as needed)
Other Installation (replace as needed)
Client Move-In |  |  | 2013-12-16